E26000006 | Peak District NP | Revised National Park Local Plan parts 1 and 2 | Yet to Start Reg 18 | 2011 | 2026 | N | N | 2011-10-07 | YES | Nitrates (March 2022) | PAS | [8 empty] | Yes | Yes | LDS Document |  | https://www.peakdistrict.gov.uk/planning/how-we-work/policies-and-guides/supporting-documents | https://www.peakdistrict.gov.uk/__data/assets/pdf_file/0020/582401/PDNP-Local-Development-Scheme-2015-2018v2.pdf | https://mhclg.sharepoint.com/:i:/s/DevelopmentPlans/EUlO_eXEhyBHqN7XS--lXesBuGxIFCjfxHazrX5M0Y6tyw?e=dqIyFr | 2016-10-01 | Jan 2023 | Preferred Issues and Options consultation | 2023-01-01 |  |  |  |  | 2024 | Draft plan consultation | [19 empty] | TBC |  |  | TBC |  |  | TBC |  |  | Unable to locate new Plan period. Timetable in published LDS is out-of-date. Timetable on website (this has been updated and delayed): 2021 – debate on broad issues and evidence gathering; 2022 – preferred issues and options with formal consultation at the end of the year; 2023 – draft plan with formal consultation at the end of the year | LDS out of date. Brief timetable on website: 2022 – writing preferred issues and options with formal consultation in January 2023 2023 – preferred options consultation 2024 - draft plan |  | 2022-08-11 |  | Robert Putnam | 2021-11-17 | 2022-08-09 | Robert Putnam |  |  | VisualPing
E06000026 | Plymouth | The Plymouth and South West Devon Plan Review | 1819 | 2014 | 2034 | N | Y | 2019-03-26 | YES | Covid-19 | [9 empty] | FALSE | Yes, but TT refers to adopted Plan | LDS Document |  | https://www.plymouth.gov.uk/planningandbuildingcontrol/localdevelopmentscheme | https://www.plymouth.gov.uk/sites/default/files/PlymouthsRevisedLocalDevelopmentScheme2015.pdf | https://mhclg.sharepoint.com/:i:/r/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Data%20Project/Short-term%20Solution/LDS%20Approach/LDS%20screen%20captures/PLY16-%20Plymouth%20LDS%202016.PNG?csf=1&e=QKDBXb | 2016-12-01 | July-August 2016 |  | 2016-07-01 |  |  |  |  | November-December 2016 |  | 2016-11-01 | [18 empty] | Sping 2017 | 2017-03-01 | 2017-03-15 | Spring/Summer 2017 | 2017-05-01 | 2017-07-31 | Winter 2017 | 2018-01-01 | 2019-03-26 | Plymouth and South West Devon Joint Local Plan 2014-2034 adopted by West Devon BC on 26 March 2019 (and adopted by South Hams DC on 21 March 2019). The impact of COVID-19 has disrupted planning services across the JLP area at each respective authority. **** Consultation on the Plymouth and South West Devon Climate Emergency Planning Policy and Guidance ends on 21 April 2022. This is a draft new planning policy and guidance that responds directly to the Climate Emergency Declarations and identifies exactly what all new development should do to meet the challenge of climate change. |  | The first version of the Plymouth and South West Devon Local Development Scheme was published in October 2019 but has become out of date. The Joint Local Plan Councils are committed to the delivery of the plan, and to keeping its policies fully up to date at all times. A review of the Joint Local Plan will be completed by 26 March 2024 at the latest. A new revised Local Development Scheme setting out the detailed timetable for the review will be produced once there is clarity about changes to the planning system. | 2022-08-08 |  | Robert Putnam |  |  |  | 2022-08-08 | A | adopted March 2019
E06000044 | Portsmouth | Portsmouth Local Plan 2038 | 2120 | 2020 | 2038 | N | N | 2012-01-24 | YES | Nitrates (since 2018) | [9 empty] | Yes | Yes | LDS Document |  | https://www.portsmouth.gov.uk/services/development-and-planning/planning-policy/local-development-scheme/ | https://www.portsmouth.gov.uk/wp-content/uploads/2022/03/Portsmouth-Local-Development-Scheme-March-2022-Accessible.pdf |  | 2022-03-01 | July 2017 | Issues & Options | 2017-07-01 | 2017-08-03 | 2017-09-28 | https://www.portsmouth.gov.uk/ext/documents-external/lplan-issues-and-options-paper-july-2017.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Portsmouth%20Aug%202017%20Issues%20&%20Options.PNG | Dec 2019 | Evidence base consultation ('Local Plan update') | 2019-12-01 | 2019-02-11 | 2019-03-25 | https://www.portsmouth.gov.uk/ext/documents-external/local-plan-update-february-2019.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Portsmouth%20Feb%202019%20local%20plan.PNG | Summer 2021 | Consultation on draft Plan (Reg 18) | 2021-07-01 | 2021-09-17 | 2021-10-31 | https://www.portsmouth.gov.uk/services/development-and-planning/planning-policy/the-local-plan/ | [8 empty] | Dec 2022 | 2022-12-01 |  | Spring 2023 | 2023-04-01 |  | 2024 / TBC | TBC |  |  | PINS Intel (April 2022): Reg 19 expected Dec 2022; Submission Spring 2023 |  | 2022-08-31 | 2022-08-11 | Robert Putnam |  | 2022-08-11 | Robert Putnam | 2022-07-28 |  | Visualping
E07000051 | Purbeck (defunct, now part of Dorset) | Purbeck Local Plan Review | 2016 | 2018 | 2034 | N | N | 2012-11-13 | YES | Nitrates (since 2018) |  |  | 2018-10-22 | 2019-01-28 | [5 empty] | Yes | Yes | LDS Document |  | https://www.dorsetcouncil.gov.uk/planning-buildings-land/planning-policy/purbeck/purbeck-local-plan-review.aspx | https://www.dorsetcouncil.gov.uk/planning-buildings-land/planning-policy/purbeck/local-plan-review-purbeck/local-development-scheme.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Data%20Project/Short-term%20Solution/LDS%20Approach/LDS%20screen%20captures/DOR19%20-%20Dorset%20LDS%20June%202019.PNG | 2018-02-01 | Jan - March 2018 | Consultation to inform DPD | 2018-02-01 | [25 empty] | Nov - Dec 2018 | 2018-11-01 | 2018-10-22 | Feb 2019 | 2019-02-01 | 2019-01-28 | Sept 2019 | 2019-09-01 |  | On 1 April 2019 Dorset Council was established, comprising the areas of East Dorset District Council, North Dorset District Council, Purbeck District Council, West Dorset District Council and Weymouth & Portland District Council. New Council to prepare a new Plan for Dorset Council. However the Purbeck Local Plan is undergoing examination. An updated schedule of the proposed MMs was published in December 2020. |  |  | 2020-02-10 |  | Robert Putnam |  |  |  |  | S | Submitted Jan 2019
E06000003 | Redcar & Cleveland | Redcar and Cleveland Local Plan | n/a | 2016 | 2032 | N | N | 2018-05-24 | YES | Nitrates (March 2022) | [9 empty] | FALSE | Yes, but TT refers to adopted Plan | LDS Document |  | https://www.redcar-cleveland.gov.uk/resident/planning-and-building/strategic%20planning/Pages/local-development-scheme.aspx | https://www.redcar-cleveland.gov.uk/resident/planning-and-building/strategic%20planning/Documents/Local%20Development%20Scheme%20Nov%202016-2019.pdf | https://mhclg.sharepoint.com/:i:/r/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Data%20Project/Short-term%20Solution/LDS%20Approach/LDS%20screen%20captures/RED15%20-%20Redcar%20and%20Cleveland%20LDS%202015.PNG?csf=1&e=w9qUQl | 2016-11-01 | May 2016 |  | 2016-05-01 | [25 empty] | December 2016 | 2016-12-01 | 2016-12-06 | March/April 2017 | 2017-03-01 | 2017-04-18 | August 2017 | 2017-08-01 | 2018-05-24 |  | No up-to-date LDS or timetable. No evidence of any work on an emerging plan having started. |  | 2022-03-29 |  | Robert Putnam | 2022-03-08 |  | Robert Putnam |  |  | adopted May 2018
E07000166 | Richmondshire | Richmondshire Local Plan 2018-2039 | 2134 | 2018 | 2039 | N | N | 2014-12-09 | YES | Nitrates (March 2022) | [9 empty] | Yes | Yes | Web-page timetable |  | https://www.richmondshire.gov.uk/planning/planning-policy/local-development-scheme/ | https://www.richmondshire.gov.uk/planning-and-climate-change/emerging-planning-policy/local-development-scheme/ |  | 2021 | September 2018 | Issues & Options | 2018-09-01 | 2018-09-03 | 2018-10-31 | https://www.richmondshire.gov.uk/media/9662/local-plan-review-issues-and-options-paper.pdf |  | Spring 2020 | Preferred Options | 2020-04-01 | 2021-05-28 | 2021-07-23 | https://www.richmondshire.gov.uk/planning-and-climate-change/emerging-planning-policy/preferred-options/?utm_campaign=&utm_content=&utm_medium=email&utm_source=govdelivery&utm_term= |  | 2021-04-01 | Preferred Options 2 | 2021-04-01 | 2021-05-01 | 2021-07-01 | [9 empty] | Jan 2023 | 2023-01-01 |  | July 2023 | 2023-07-01 |  | TBC | TBC |  | PINS Intel (August 2022): Publication expected Jan 2023 (was Nov 2022); Submission for examination May or July 2023 | PINS Intel (August 2022): Publication expected Jan 2023 (was Nov 2022); Submission for examination May or July 2023 |  | 2022-01-19 | 2021-10-11 | Robert Putnam | 2022-01-19 | 2022-08-24 | Robert Putnam | 2022-08-24 |  | Visualping
E07000064 | Rother | Rother Local Plan 2039 | Yet to Start Reg 18 | 2019 | 2039 | N | N | 2014-09-29 | YES | OTHER (change of plan scope) | [9 empty] | Yes | Yes | LDS Document |  | http://www.rother.gov.uk/LDS | https://www.rother.gov.uk/wp-content/uploads/2021/03/Local-Development-Scheme_2021_Final-.pdf |  | 2021-03-01 | Q3 2021/22 | Draft Plan | 2021-11-01 | Jan-Feb 2023 | [24 empty] | Dec 2022 | 2022-12-01 |  | April 2023 | 2023-04-01 |  | Mar/July 2024 | 2024-03-01 |  | First Reg 18 consultation scheduled for Dec 2019 - Jan 2020, but no evidence of it having commenced. Now looks like they will not be doing any consultation until Summer Autumn 2021 on options. Revising evidence base and about to prepare new LDS well behind time. Submission could be 22/23 as at very early stage. Delay due to change of plan scope. The plan period is currently proposed to be 2019 to 2039. This is possibly tight for the strategic policies to look ahead over a minimum 15 year period from adoption (para 22 of the Framework), especially if the examination becomes protracted. | Latter stages of timetable (Reg 19 onwards) taken from Inspector's note of advisory meeting in October 2021: Reg 19 expected December 2022; Submission Feb/March 2023; and Adoption is likely in March-July 2024. PINS Intel (August 2022): R19 Dec 2022; Submission April 2023. *** However, website says that consultation that was supposed to happen this Spring 2022 (Reg 18) is delayed to Jan/Feb 2023. |  | 2022-03-29 | 2021-08-19 | Robert Putnam |  | 2022-08-24 | Robert Putnam | 2022-08-24 |  | Visualping
E07000188 | Sedgemoor | Sedgemoor Local Plan | 1811 | 2011 | 2032 | N | N | 2019-02-20 | YES | Nitrates (since 2018) | [9 empty] | FALSE | Yes, but TT refers to adopted Plan | LDS Document |  | https://www.sedgemoor.gov.uk/article/1286/Local-Development-Scheme | https://www.sedgemoor.gov.uk/media/3611/Local-Development-Scheme-2018-2021/pdf/Local_Development_Scheme_Oct_2018.pdf?m=636759086632400000 | https://mhclg.sharepoint.com/:i:/r/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Data%20Project/Short-term%20Solution/LDS%20Approach/LDS%20screen%20captures/SED18%20-%20Sedgemoor%20LDS%202018.PNG?csf=1&e=XVkFJh | 2018-10-01 | October 2015-August 2016 |  | 2015-10-01 | [25 empty] | January 2017 | 2017-01-01 | 2017-01-30 | August 2017 | 2017-08-01 | 2017-08-01 | January-2019 | 2019-01-01 | 2019-02-20 | No work underway on a review due to unitarisation (Somerset) on 1 April 2023. Sedgemoor's Plan was adopted oin 2019 and will remain in place until replaced by a new plan prepared by the new unitary authority. | No work underway on a review due to unitarisation (Somerset) on 1 April 2023. Sedgemoor's Plan was adopted in 2019 and will remain in place until replaced by a new plan prepared by the new unitary authority. |  | 2019-04-09 |  | Eloise Maguire |  | 2022-04-21 | Robert Putnam |  | A | adopted February 2019
E07000111 | Sevenoaks | Sevenoaks Local Plan | Yet to Start Reg 18 |  |  | N | N | 2011-02-22 | YES | Previous emerging plan found non-legally compliant 2 March 2020. | [9 empty] | Yes | Yes | LDS Document |  | https://www.sevenoaks.gov.uk/directory_record/8/local_development_scheme | https://www.sevenoaks.gov.uk/downloads/file/790/local_development_scheme |  | 2022-07-01 | Autumn 2022 | Reg 18 consultation | 2022-10-01 |  |  |  |  | Autumn 2023 | Draft Plan (Reg 18) | 2023-10-01 | [18 empty] | Spring 2024 | 2024-04-01 |  | Summer 2024 | 2024-08-01 |  | TBC | TBC |  | 1st Reg 18 in September/October 2022; 2nd Reg 18 in Autumn 2023; Reg 19 Spring 2024 and Submission summer 2024. | 1st Reg 18 in September/October 2022; 2nd Reg 18 in Autumn 2023; Reg 19 Spring 2024 and Submission summer 2024. |  |  | 2022-08-12 | Robert Putnam |  | 2022-08-12 | Robert Putnam | 2022-08-12 |  | VisualPing
E06000051 | Shropshire | Shropshire Local Plan Review 2016-2038 | 2011 | 2016 | 2036 | N | N | 2011-02-24 | YES | Nitrates (March 2022) |  |  | 2020-12-18 | 2021-09-03 | [5 empty] | Yes | Yes | LDS Document |  | https://shropshire.gov.uk/planning-policy/local-planning/local-plan-review/local-development-scheme-lds/ | https://shropshire.gov.uk/media/19054/local-development-scheme-march-2021.pdf |  | 2021-03-01 | January 2017 |  | 2017-01-01 | 2017-01-23 | 2017-03-20 | https://shropshire.gov.uk/media/3673/issues-and-strategic-options-consultation-document.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Shropshire%20Jan%202017%20-%20FIRST.PNG | October 2017 - September 2019 | Strategic Sites | 2017-10-01 | 2017-10-27 | [Sept 2019] | https://shropshire.gov.uk/get-involved/strategic-sites-consultation/ | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Shropshire%20July%202019%204th%20consultation.PNG | [14 empty] | December 2020 | 2020-12-01 | 2020-12-01 | July 2021 | 2021-07-01 | 2021-09-03 | July 2022 | 2022-07-01 |  | Additional Regulation 18 Pre-Submission Draft of the Shropshire Local Plan consultation from Monday 3 August 2020 - Wednesday 30 September 2020. All responses should be received by the council by 5pm on Wednesday 30 September 2020. Updated LDS published in Dec 2020 with a revised timescale for the Reg 19 publication and subsequent submission and adoption. Reg 19 pre-submission draft was consulted on between 18 Dec 2020 - 26 February 2021. | Plan period extended to 2038 at publication stage. Published 18 Dec 2020. Submitted 3 September 2021 (was expected July 2021, before that April 2021); Adoption expected July 2022 (was May 2022). |  | 2022-05-03 | 2021-07-07 | Robert Putnam | 2021-04-16 | 2021-10-06 | Robert Putnam |  | S | Submitted Sept 2021; Visualping
E06000039 | Slough | Local Plan for Slough 2016-2036 | 2156 | 2016 | 2036 | N | N | 2008-12-16 | YES | OTHER | PAS | [8 empty] | Yes | Yes | Web-page timetable |  | https://www.slough.gov.uk/planning-policy/emerging-local-plan-slough-2016-2036?documentId=639&categoryId=20131 | https://www.slough.gov.uk/downloads/file/65/local-plan-development-scheme-2019 | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/LDS%20&%20Reg%2018%20Monitoring/LDS%20Screenshots/SLO19%20-%20Slough%20updated%20TT%20Oct%202019.PNG | 2019-04-01 | Jan 2017 |  | 2017-01-01 | 2017-01-16 | 2017-02-27 | http://www.slough.gov.uk/downloads/SBC_IO_ConsultatioDoc160117.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Slough%20Issues%20&%20Options%20Jan%202017.PNG | Feb 2020 | Preferred Options (Preferred Spatial Strategy) | 2020-02-01 | 2020-11-09 | 2021-01-11 | https://slough.citizenspace.com/ |  | 5 November 2021 | Green Belt and Sustainability (Reg 18) | 2021-11-05 | 2021-11-05 | 2021-12-17 | https://www.slough.gov.uk/planning/consultation-proposed-release-green-belt-sites-family-housing | [8 empty] | Feb 2023 | 2023-02-01 |  | April 2023 | 2023-04-01 |  | TBC | TBC |  | Second Reg 18 consultation closed Jan 2021. Further round of consultation on release of Green Belt land for family housing and Sustainability Appraisal running from 5 November 2021 to 17 December 2021. Website indicates that milestones wil be delayed and not accord with schedule in LDS (Publication was Summer 2021/Submission was Winter 2021/Adoption was Summer 2022). Website timetable indicates Publication and examination in 2022 & 2023 TBC. Work on local plan paused due to budget issues | PINS Intel (August 2022); Reg 19 Feb 2023; Submission April 2023 |  | 2022-05-13 |  | Robert Putnam | 2022-06-27 | 2022-08-24 | Robert Putnam | 2022-08-24 |  | VisualPing
E07000246 | Somerset West and Taunton | Local Plan 2040 | 2119 | 2020 | 2040 | N | N | new LPA | YES | Other Nitrates (since 2018) | [9 empty] | Yes | Yes | LDS Document |  | https://www.somersetwestandtaunton.gov.uk/planning-policy/local-development-scheme/ | https://www.somersetwestandtaunton.gov.uk/media/1953/district-wide-lp-ctte-report-lds-appendix-1-july-2019-final-published-version.pdf |  | 2019-07-01 | Q3 19/20 | Issues and Options | 2019-11-01 | 2020-01-01 | 2020-03-01 | https://yoursay.somersetwestandtaunton.gov.uk/local-plan/issues-and-options/ | [22 empty] | Q2 2020/21 | 2020-08-01 |  | Q3 2020/21 | 2020-11-01 |  | Q3 2021/22 | 2021-11-01 |  | On 21 July 2021, the Government announced that, subject to Parliamentary approval, a new unitary council for Somerset will be formed on 1 April 2023 to replace the existing county and district councils. However, Exmoor National Park Authority will remain as the Local Planning Authority for the area of National Park within Somerset. Given these timescales and the numerous stages in Local, Mineral and Waste Plan preparation the existing councils will therefore no longer be progressing new plans through the statutory process based on their individual geographies. Existing county and district councils are working closely to scope the content and timescales for new Development Plan(s) to be prepared in the future as part the single unitary council. This includes ongoing work to progress and align key evidence base documents. Relevant documents, including an updated Local Development Scheme (LDS) for the new Somerset Council will be published in due course as the councils work through the transitional arrangements. | Reg 18 consultation (only one) completed March 2020. Publication scheduled for July 2020 (QTR2 20/21) but delayed due to Covid-19. All milestones under review. PINS Intel: Currently have Publication estimated as 01/11/21 with Submission 01/01/22 however LPA state timetable under review. WORK STOPPED DUE TO UNITARISATION (SOMERSET) ON 1 APRIL 2023. |  | 2022-08-11 |  | Robert Putnam | 2021-08-06 | 2022-04-21 | Robert Putnam |  | Work Stopped | Visualping
E07000039 | South Derbyshire | South Derbyshire Local Plan | n/a | 2011 | 2028 | N | N | 2016-06-13 | YES | Nitrates (March 2022) | [9 empty] | FALSE | Yes, but refers to something else | LDS Document |  | https://www.southderbyshire.gov.uk/our-services/planning-and-building-control/planning/planning-policy/monitoring | https://www.southderbyshire.gov.uk/assets/attach/4982/LDS%202018%20-%202021.pdf |  | 2018-05-01 | [37 empty] | South Derbyshire Local Plan adopted June 2016 (Pt 1) and Nov 2017 (part 2). Current LDS covers supplementary docs only. | Call for Sites undertaken between 3 Oct 2019 and 12 Dec 2019. |  | 2021-09-17 |  | Robert Putnam | [5 empty] | Visualping
E26000010 | South Downs | South Downs Local Plan | 1857 | 2014 | 2033 | N | N | 2019-07-02 | YES | Nitrates (since 2018) | [9 empty] | FALSE | Yes, but TT refers to adopted Plan | LDS Document |  | https://www.southdowns.gov.uk/planning/national-park-local-plan/ | https://www.southdowns.gov.uk/wp-content/uploads/2018/10/LDS-sixth-revision.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Data%20Project/Short-term%20Solution/LDS%20Approach/LDS%20screen%20captures/SDO-2018%20South%20Downs%20LDS.png | 2018-10-01 | [30 empty] | 2017-09-26 | April 2018 | 2018-04-01 | 2018-04-27 | May 2019 | 2019-05-01 | 2019-07-02 | Reg 18 and Reg 19 consultation dates not provided in LDS (past dates) |  |  | 2019-04-01 |  | Max Laverack |  |  |  |  | A | adopted July 2019
E06000025 | South Gloucestershire | WECA Spatial Development Strategy (SDS) |  | 2022 | 2042 | N | SDS | 2013-12-11 | YES | lack of agreement | [9 empty] | Yes | Yes | LDS Document |  | https://www.westofengland-ca.gov.uk/what-we-do/planning-housing/spatial-development-strategy/ | https://beta.bathnes.gov.uk/sites/default/files/2021-08/LDS%20July%202021%20Final%20-%20accessible.pdf |  | 2021-12-01 | Second Half of 2021 | Draft SDS Public consultation | 2021-07-01 | [25 empty] | Spring 2022 | 2022-04-01 |  | Spring 2023 | 2023-04-01 |  | TBC | TBC |  | Mayor of WoE has written to SoS stating that he has halted work on SDS due to lack of agreement by S Glos. S Glos have met with Simon G to discuss. |  | Statutory consultation on draft plan scheduled for Spring 2022 but missed. Work halted due to lack of agreement by South Gloucestershire (who want to progress work on their own plan). | 2022-03-08 |  | Robert Putnam | 2022-03-08 |  | Robert Putnam | 2022-06-28 |  | VisualPing
E07000044 | South Hams | The Plymouth and South West Devon Plan Review | 1819 | 2014 | 2034 | N | Y | 2019-03-21 | YES | COVID-19 | [9 empty] | FALSE | Yes, but TT refers to adopted Plan | LDS Document |  | https://www.southhams.gov.uk/article/3869/How-We-Make-Our-Plans | https://www.southhams.gov.uk/media/1976/Joint-Local-Plan-LDS-December-2016/pdf/161219_JLP_Local_Development_Scheme_FINAL.pdf | https://mhclg.sharepoint.com/:i:/r/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Data%20Project/Short-term%20Solution/LDS%20Approach/LDS%20screen%20captures/SHA16%20-%20South%20Hams%20LDS%202016.PNG?csf=1&e=kCuUTR | 2016-12-01 | July-August 2016 |  | 2016-07-01 |  |  |  |  | November-December 2016 |  | 2016-11-01 | [18 empty] | Sping 2017 | 2017-03-01 | 2017-03-15 | Spring/Summer 2017 | 2017-05-01 | 2017-07-31 | Winter 2017 | 2017-12-01 | 2019-03-21 | Plymouth and South West Devon Joint Local Plan 2014-2034 adopted by West Devon BC on 26 March 2019 (and adopted by South Hams DC on 21 March 2019). The impact of COVID-19 has disrupted planning services across the JLP area at each respective authority. |  | The first version of the Plymouth and South West Devon Local Development Scheme was published in October 2019 but has become out of date. The Joint Local Plan Councils are committed to the delivery of the plan, and to keeping its policies fully up to date at all times. A review of the Joint Local Plan will be completed by 26 March 2024 at the latest. A new revised Local Development Scheme setting out the detailed timetable for the review will be produced once there is clarity about changes to the planning system. | 2022-08-08 |  | Robert Putnam |  |  |  | 2022-08-08 | A | adopted March 2019
E07000031 | South Lakeland | South Lakeland Local Plan | 2281 | 2020 | 2040 | N | N | 2010-10-20 | YES | Nitrates (March 2022) | PAS | [8 empty] | Yes | Yes | LDS Document |  | https://www.southlakeland.gov.uk/planning-and-building/south-lakeland-local-plan/local-development-scheme-lds/ | https://www.southlakeland.gov.uk/media/7644/issues-and-options-report.pdf |  | 2021-06-01 | June 2021 | Issues and Options and second Call for Sites | 2021-06-01 | 2021-06-30 | 2021-10-29 | https://www.southlakeland.gov.uk/planning-and-building/south-lakeland-local-plan/local-plan-review/2021-issues-and-options-and-second-call-for-sites/ |  | Summer 2022 | Draft Plan | 2022-07-01 | [18 empty] | Spring 2023 | 2023-04-01 |  | Autumn 2023 | 2023-07-01 |  | Spring 2024 | 2024-04-01 |  |  | PINS Intel (August 2022): Reg 19 April 2023; Submission July 2023. Intel trumps timetable in Issues and Options document (June 2021) which has a Reg 18 on draft Plan in Summer 2022; Reg 19 Spring 2023; Submission Autumn 2023 and Adoption in Spring 2024. |  | 2022-08-25 |  | Robert Putnam |  | 2022-08-30 | Robert Putnam | 2022-08-30 |  | VisualPing
E07000189 | South Somerset | Local Plan Review 2020 - 2040 | 2158 | 2020 | 2040 | N | N | 2015-03-05 | YES | Nitrates (since 2018) | [9 empty] | Yes | Yes | Web-page timetable |  | https://www.southsomerset.gov.uk/your-council/your-council-plan-and-strategies/planning-policy/local-plan-review-2016-2036/ | https://www.southsomerset.gov.uk/your-council/your-council-plan-and-strategies/planning-policy/local-plan-review-2016-2036/ | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/LDS%20&%20Reg%2018%20Monitoring/LDS%20Screenshots/SSO20%20-%20South%20Somerset%20website%20TT%202020.PNG | 2020-07-01 | Oct 2017 - Jan 2018 | Issues & Options | 2017-11-01 | 2017-10-26 | 2018-01-11 | https://www.southsomerset.gov.uk/media/1314/early_review_local_plan_issues_and_options_merged_v12_-_final.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/South%20Somerset%20Issues%20&%20Options%20Oct%202017.PNG | Mid 2019 | Preferred Options | 2019-06-01 | 2019-06-28 | 2019-09-18 | https://www.southsomerset.gov.uk/your-council/your-council-plan-and-strategies/planning-policy/local-plan-review-2016-2036/ | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/South%20Somerset%20Preferred%20Options%20June%202019.PNG | [14 empty] | mid 2022 | 2022-06-01 |  | early 2023 | 2023-01-01 |  | TBC | TBC |  | On 21 July 2021, the Government announced that, subject to Parliamentary approval, a new unitary council for Somerset will be formed on 1 April 2023 to replace the existing county and district councils. However, Exmoor National Park Authority will remain as the Local Planning Authority for the area of National Park within Somerset. Given these timescales and the numerous stages in Local, Mineral and Waste Plan preparation the existing councils will therefore no longer be progressing new plans through the statutory process based on their individual geographies. Existing county and district councils are working closely to scope the content and timescales for new Development Plan(s) to be prepared in the future as part the single unitary council. This includes ongoing work to progress and align key evidence base documents. Relevant documents, including an updated Local Development Scheme (LDS) for the new Somerset Council will be published in due course as the councils work through the transitional arrangements. | Reg 18 stages now completed. Timetable is taken from website timeline (April 2017 LDS is out of date and has been ignored). Preferred Options Reg 18 stage completed Sept 2019. According to web-based TT, Reg 19 now expected mid-2022 (was early/mid 2021). Submission early 2023 (was late 2021). WORK STOPPED DUE TO UNITARISATION (SOMERSET) ON 1 APRIL 2023. |  | 2022-05-03 |  | Robert Putnam | 2021-11-19 | 2022-04-21 | Robert Putnam |  | Work Stopped | Visualping
E06000045 | Southampton | Southampton City Vision | 2140 | 2016 | 2036 | N | N | 2015-03-18 | YES | Covid-19 Nitrates (since 2018) | [9 empty] | Yes | Yes | LDS Document |  | https://www.southampton.gov.uk/planning/planning-policy/emerging-plans/cityvision/documentslibrary/ | https://www.southampton.gov.uk/media/w45nmcyk/updated-local-development-scheme.pdf |  | 2021-12-01 | January - March 2020 | Issues & Options | 2020-01-01 | 2020-02-10 | 2020-05-31 | http://www.southampton.gov.uk/planning/planning-policy/emerging-plans/cityvision/haveyoursay.aspx |  | Oct - Nov 2020 | Preferred Options | 2020-10-01 |  |  |  |  | Summer 2022 | Draft Plan with Options | 2022-07-01 | [11 empty] | Summer 2023 | 2023-07-01 |  | December 2023 | 2023-12-01 |  | TBA | TBA |  | Core Strategy Partially Reviewed and adopted March 2015. Council working on new Plan to 2036 (merging CS and SAP into one). The first consultation on Southampton City Vision (the new Local Plan) took place from 10 February 2020 to 31 May 2020 (extended from 19 April 2020 due to disruption caused by Covid-19). Southampton City Vision will set out the future development of new homes, work spaces, infrastructure and facilities across the city over the next 20 years and beyond. | Reg 18 consultation on Draft Plan with Options scheduled for Summer 2022; Reg 19 Summer 2023; Submission December 2023. No estimation of Adoption provided in timetable. |  | 2022-08-22 | 2022-03-29 | Robert Putnam | 2022-08-09 | 2022-03-29 | Robert Putnam |  |  | Visualping
E07000240 | St Albans | St Albans City and District Local Plan 2020 - 2038 (NEW PLAN) | TBA | 2020 | 2038 | N | N | none | YES | Previous plan withdrawn. Current Plan significantly delayed. | [9 empty] | Yes | Yes | LDS Document |  | https://www.stalbans.gov.uk/local-development-scheme-2020-2023 | https://www.stalbans.gov.uk/sites/default/files/attachments/Local%20Development%20Scheme%202020-2023.pdf |  | 2021-01-01 | Jan - Feb 2022 |  | 2022-01-01 | [25 empty] | Nov - Dec 2022 | 2022-11-01 |  | Spring/Summer 2023 | 2023-04-01 |  | End 2023 | 2023-12-01 |  | In Spring 2018, St Albans, Dacorum, Hertsmere, Three Rivers, and Watford Councils gave formal endorsement to begin work on a Joint Strategic Plan (JSP) for South West Hertfordshire. Work on the JSP will progress in alignment to an agreed Statement of Common Ground (SoCG). This is currently being prepared by the joint authorities. 3.8 Each council will still be responsible for preparing its own Local Plan, but the JSP will provide the platform to consider how the challenges of growth in the wider South West Hertfordshire area can be addressed longer term (i.e. 2036 to 2050). St Albans Local Plan: Previous local plan withdrawn from examination November 2020. New LDS Jan 2021. First and only Reg 18 Jan/Feb 2022; Reg 19 Nov 2022; Submission Spring/Summer 2023; Adoption end 2023. South West Herts JSP: No timetable yet determined for South West Herts JSP. | Previous local plan withdrawn from examination November 2020. New LDS Jan 2021. First and only Reg 18 Jan/Feb 2022; Reg 19 Nov 2022; Submission Spring/Summer 2023; Adoption end 2023. New timetable to be voted on February 2022. Council is considering pushing back the adoption of its new local plan by three years due to resourcing pressures. | The first consultation on the document is due to take place in early September. | 2021-10-11 |  | Robert Putnam |  |  |  | 2022-01-17
E07000197 | Stafford | New Stafford Borough Local Plan 2020-2040 | 2219 | 2020 | 2040 | N | N | 2014-06-19 | YES | Covid-19 PWP | [9 empty] | Yes | Yes | LDS Document |  | https://www.staffordbc.gov.uk/local-development-scheme | https://www.staffordbc.gov.uk/local-development-scheme-2021-pdf |  | 2021-11-01 | July 2018 - September 2019 | Scoping the Issues | 2018-07-01 | 2018-07-18 | 2018-09-18 | https://www.staffordbc.gov.uk/sites/default/files/cme/DocMan1/Planning%20Policy/New%20Local%20Plan%20Scoping%20the%20Issues/Scoping%20the%20Issues%20Report%20for%20Consultation%20July%202018.pdf |  | Feb 2020 | Issues and Options | 2020-04-21 | 2020-02-03 | 2020-04-21 | https://www.staffordbc.gov.uk/local-plan-review- |  | Oct - Dec 2022 | Preferred Options | 2022-10-01 | [11 empty] | July - Sept 2023 | 2023-07-01 |  | Nov 2023 | 2023-11-01 |  | Oct 2024 | 2024-10-01 |  | The New Local Plan 2020-2040 will fully replace the Plan for Stafford Borough (PFSB) and the PFSB Part 2 with a new development strategy, site allocations and Development Management policies. - Commencement July 2017 - Issues and Options July 2018 to April 2020 - Preferred Options June & July 2022 - Publication July to September 2023 - Submission November 2023 - Examination February 2024 - Adoption October 2024 | Preferred Options June & July 2022; Publication July to September 2023; Submission November 2023; Examination February 2024; Adoption October 2024. The Preferred Option Report stage has been re-scheduled for later in the year. It is anticipated that the consultation will take place from October to December 2022. |  | 2022-08-31 | 2021-12-10 | Robert Putnam | 2022-08-19 | 2022-06-24 | Robert Putnam |  |  | VisualPing
E08000007 | Stockport | Stockport Local Plan | 2170 | 2020 | 2035 | N | N | 2011-03-17 | YES | National uncertainty (new PM & new policies) | [9 empty] | Yes | Yes | LDS Document |  | https://www.stockport.gov.uk/stockport-local-development-scheme/introduction-stockport-local-development-scheme | https://assets.ctfassets.net/ii3xdrqc6nfw/2ABYaphVngJMkE90uAKxgr/81f5bf278f13b2fb74ea0a09cab1e6dc/Stockport_Local_Development_Scheme_November_2021.pdf |  | 2021-11-01 | July-Oct 2017 | Issues & Options | 2017-07-01 | 2017-07-01 | 2017-10-01 |  |  | Summer/Autumn 2022 | Preferred Options | 2022-07-01 | [18 empty] | Summer/Autumn 2023 | 2023-07-01 |  | Winter 2023/2024 | 2024-01-01 |  | Autumn 2024 | 2024-10-01 |  | Stockport officers have approached both PAS and MHCLG officials stating that they have cross party support for getting a Local Plan in place by Dec 2023. A Local Development Scheme was published on 19 March which indicates they will adopt a Stockport Plan before end of 2023. We are proposing to provide PAS support to assist with LP programme and resource planning. We have met with Stockport Officers and they will provide further updates regarding their progress on plan preparation at an official level meeting on 18 November. William Wragg MP and Mary Robinson MP have written to the SoS asking that the 2023 deadline be extended a year for Stockport and asking that they have a lower LHN figure. (Leads – Sara Lewis/Andrew Langley). | First Reg 18 (Issues and Options) completed October 2017. Second Reg 18 (Preferred Options) scheduled for Summer/Autumn 2022 (was Autumn 2021). Publication Summer/Autumn 2023 (was Winter/Spring 2022); Submission Winter 2023/2024 (was Autumn 2022). Adoption Autumn 2024. *** update 2 Sept 2022 - Stockport have announced that the consultation due in September 2022 has been postponed |  | 2021-10-11 | 2021-12-17 | Robert Putnam |  | 2021-12-17 | Robert Putnam | 2021-12-17 |  | E-mail
E06000004 | Stockton-on-Tees | Stockton on Tees Borough Local Plan | 1856 | 2017 | 2032 | N | N | 2019-01-30 | YES | Nitrates (March 2022) | [9 empty] | FALSE | Yes, but TT refers to adopted Plan | LDS Document |  |  | https://www.stockton.gov.uk/media/7139/local-development-scheme-2016-2019.pdf | https://mhclg.sharepoint.com/:i:/s/DevelopmentPlans/EYHianW9MDhGn9C0vx2r_lgBSGYbRRXbUeRaGUIkLoIS2A?e=ebS92f | 2016-07-01 | Autumn 2016 |  | 2016-10-01 | [25 empty] | Summer 2017 | 2017-07-01 | 2017-09-25 | Autumn 2017 | 2017-10-01 | 2017-12-21 | Summer 2018 | 2018-07-01 | 2019-01-30 | Local Plan adopted Jan 2019. No evidence of new LDS or review. |  |  | 2019-04-01 |  | Robert Putnam |  |  |  |  | A | adopted January 2019
E06000021 | Stoke on Trent | Stoke-on-Trent Local Plan | 2136 | 2020 | 2040 | N | N | 2009-10-01 | YES | Withdrawn from Joint Plan | [9 empty] | Yes | Yes | Web-page timetable |  | https://www.stoke.gov.uk/info/20071/joint_local_plan/317/joint_local_plan_timetable |  | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/LDS%20&%20Reg%2018%20Monitoring/LDS%20Screenshots/STOT2021%20Stoke%20on%20Trent%20TT%20Feb%202021.PNG | 2021-02-01 | Spring 2021 | Issues and Options | 2021-04-01 | 2021-05-10 | 2021-06-21 | https://www.stoke.gov.uk/info/20071/stoke-on-trent_local_plan/429/issues_and_options_consultation |  | Winter 2021 | Draft Local Plan | 2022-01-01 | [18 empty] | Spring 2022 | 2022-04-01 |  | Summer 2022 | 2022-07-01 |  | TBC |  |  | Reg 18 consultation ongoing. First Reg 18 ("Issues & Options" began 10 May and closed 21 June 2021. Second Reg 18 ("Draft Plan") scheduled for Winter 2021 and Publication expected Spring 2022. Submission Summer 2022. Web-based TT is out of date. | Delayed. LPA working on new LDS and timetable. |  | 2022-09-20 |  | Robert Putnam | 2022-09-02 | 2021-05-11 | Robert Putnam |  |  | VisualPing & e-mail
E07000082 | Stroud | District Local Plan | 2260 | 2020 | 2040 | N | N | 2015-11-19 | YES | Planning White Paper |  | YES | 2021-05-26 | 2021-10-25 | [5 empty] | Yes | Yes | LDS Document |  | https://www.stroud.gov.uk/environment/planning-and-building-control/planning-strategy/local-development-scheme | https://www.stroud.gov.uk/media/1411544/local-development-scheme-2020.pdf |  | 2020-10-15 | Autumn 2017 | Issues | 2017-10-01 | 2017-10-11 | 2017-12-05 | https://www.stroud.gov.uk/environment/planning-and-building-control/planning-strategy/stroud-district-local-plan-review/local-plan-review-issues-and-options | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Stroud%20Issues%20&%20Options%20Oct%202017.PNG | Autumn 2018 | Emerging Strategy | 2018-10-01 | 2018-11-16 | 2019-01-18 | https://www.stroud.gov.uk/environment/planning-and-building-control/planning-strategy/stroud-district-local-plan-review |  | Autumn 2019 | Draft plan consultation | 2019-10-01 | 2019-11-20 | 2020-01-22 | http://www.stroud.gov.uk/info/Draft_Plan_2019.pdf |  | Autumn 2020 | Additional Housing Options | 2020-10-01 | 2020-10-21 | 2020-12-16 | https://www.stroud.gov.uk/media/1287256/additional-housing-options-consultation-paper-16-10-20-for-web.pdf |  | Spring 2021 | 2021-04-01 | 2021-05-26 | Spring 2021 | 2021-04-01 | 2021-10-25 | Autumn 2022 | 2022-09-01 |  |  | Additional (fourth) Reg 18 stage closed December 2020. Published 26 May 2021. Submission (was Winter 2020/21) now Spring 2021; Adoption (was Winter 2021/20) now Autumn 2022. Reg 19 consultation 27th May and 21st July 2021 now closed. Submitted on 25 October 2021. |  | 2020-08-19 | 2021-04-01 | Robert Putnam |  | 2021-04-01 | Robert Putnam | 2021-08-09 | S | Submitted Oct 2021; VisualPing
E07000214 | Surrey Heath | Surrey Heath Local Plan | 2160 | 2019 | 2038 | N | N | 2012-02-01 | YES | COVID-19 | PAS | [8 empty] | Yes | Yes | LDS Document |  | https://www.surreyheath.gov.uk/residents/planning/planning-policy/planning-and-supplementary-planning-documents/local-development | https://www.surreyheath.gov.uk/sites/default/files/documents/council/Local%20Development%20Scheme%202022.docx.pdf |  | 2022-02-01 | June 2018 | Issues and Options (non-Reg 18) | 2018-06-01 | 2018-06-04 | 2018-07-30 | https://consult.surreyheath.gov.uk/consult.ti/LPIO2018/consultationHome | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Surrey%20Heath%20June%202018.PNG | Oct - Nov 2021 | Draft Plan & Draft Sustainability Appraisal/Strategic Environmental Assessment AKA Preferred Options | 2021-10-01 | 2022-03-14 | 2022-05-09 | https://www.surreyheath.gov.uk/sites/default/files/documents/residents/planning/planning-policy/LocalPlan/Draft%20Surrey%20Heath%20Local%20Plan%20-%20Preferred%20Options%20%282019%20-%202038%29%20%28NFW%29.pdf | [15 empty] | Jan - Feb 2023 | 2023-01-01 |  | June 2023 | 2023-06-01 |  | December 2023 | 2023-12-01 |  |  | Progress had been impacted by Covid-19. Final Reg 18 consultation March 2022. Reg 19 expected Jan 2023 (was May 2022); Submission June 2023 (was Oct 2022); Adoption Dec 2023 (was July 2023). PINS Intel (April 2022) corroborates timetable. |  | 2020-12-07 | 2022-07-29 | Robert Putnam |  | 2022-07-29 | Robert Putnam | 2022-07-29 |  | VisualPing
E07000113 | Swale | Local Plan | 2257 | 2022 | 2038 | N | N | 2017-07-26 | YES | Nitrates (since 2018) |  | YES. cmt to review with April 2022 adoption | 2021-02-08 | [6 empty] | Yes | Yes | LDS Document |  | https://www.swale.gov.uk/the-emerging-local-plan/ | https://services.swale.gov.uk/assets/Planning%20Policy%202019/LDS_JULY_22.pdf |  | 2022-07-01 | 27 April - 8 June 2018 | Scoping Issues (aka "Looking Ahead") | 2018-06-01 | 2018-04-27 | 2018-06-08 | https://swale-consult.objective.co.uk/kse/event/32636/section/4850459 | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Swale%20Reg%2018%20April%202018.PNG | 29 Oct 2021 | Issues and Options (new version) | 2021-10-29 | 2021-10-29 | 2021-11-29 | https://swale.gov.uk/planning-and-regeneration/local-plans/local-plan-review/public-consultation | [15 empty] | Oct - Dec 2022 | 2022-10-01 |  | Feb - March 2023 | 2023-02-01 |  | Feb 2024 | 2024-02-01 |  | New coalition in control of council after May 2019 elections. New Council looking to amend the Local Plan. The new Reg 19 publication stage is now expected in October 2022 (was Spring 2022). | Published 8 February 2021. Submission had been expected in August 2021 but Swale are not proceeding with this version of the plan and are re-consulting (Reg 18) on a different version. The Reg 18 Issues and Preferred Options consultation ran from 29 October 2021 until 29 November 2021. The new Reg 19 publication stage is now expected in October 2022 (was Spring 2022). |  | 2021-03-02 | 2022-08-10 | Robert Putnam | 2021-08-09 | 2022-08-10 | Robert Putnam | 2022-02-11 | P1 | Published Feb 2021, but re-consulting on different version.
E06000030 | Swindon | Swindon Borough Local Plan Review | 2226 | 2016 | 2036 | N | N | 2015-03-26 | YES | Nitrates (March 2022) |  |  | 2021-07-29 | [6 empty] | Yes | Yes | LDS Document |  | https://www.swindon.gov.uk/downloads/file/8014/swindon_local_development_scheme | https://www.swindon.gov.uk/download/downloads/id/8014/swindon_local_development_scheme.pdf |  | 2022-03-01 | Nov 2017 | Scope and Issues | 2017-11-01 | 2017-11-07 | 2017-12-19 | https://swindon-consult.objective.co.uk/portal/lpr/io/lprio?pointId=4756247 |  | Summer 2019 | Preferred Options | 2019-06-01 | 2019-06-01 | [17 empty] | December 2022 | 2022-12-01 |  | July 2023 | 2023-07-01 |  | Q4 2024 | 2024-11-01 |  | Review was first published on 17 December 2019, and second time July 2021. Are now doing a further, third Reg 19 consultation December 2022. | PINS Intel: Third Publication (Reg 19) scheduled for December 2022; Submission expected July 2023. Adoption expected Q4 2024. |  | 2021-03-24 | 2022-08-10 | Robert Putnam |  | 2022-08-10 | Robert Putnam | 2022-08-10 | P | Published Dec 2019 and July 2021. To re-publish (3rd) Dec 2022.
E06000020 | Telford and Wrekin | Telford and Wrekin Local Plan Review | 2171 | 2020 | 2040 | N | N | 2018-01-11 | YES | COVID-19 | [9 empty] | Yes | Yes | LDS Document |  | https://www.telford.gov.uk/info/20451/development_plans/542/local_development_scheme | https://www.telford.gov.uk/download/downloads/id/1447/local_development_scheme_2020_-_2023.pdf |  | 2020-01-01 | Summer 2020 | Issues & Options | 2020-07-01 | 2020-10-12 | 2021-01-08 | https://www.telford.gov.uk/info/20451/development_plans/3979/review_of_the_telford_and_wrekin_local_plan/2 |  | Spring 2021 | Preferred Strategy | 2021-04-01 | [18 empty] | Autumn 2021 | 2021-10-01 |  | TBC | TBC |  | TBC | TBC |  | Reg 18 consultations delayed by Covid-19. | Reg 18 consultations delayed by Covid-19. First Reg 18 consultation (issues and options) closed Jan 2021. Second Reg 18 (preferred strategy) was scheduled for Spring 2021 but likely to be delayed. Publication scheduled for Autumn 2021. Both Submission and Adoption TBC. |  | 2021-10-11 |  | Robert Putnam | 2021-03-16 |  | Robert Putnam
E07000093 | Test Valley | Local Plan 2040 | 2161 | 2020 | 2040 | N | N | 2016-01-27 | YES | Nitrates (since 2018) | [9 empty] | Yes | Yes | LDS Document |  | https://www.testvalley.gov.uk/planning-and-building/planningpolicy/lds | https://democracy.testvalley.gov.uk/documents/s17344/Test%20Valley%20LDS%20-%20Annex.pdf |  | 2021-09-01 | 2018 Q3 | Issues & Options | 2018-11-01 | 2018-07-06 | 2018-09-14 | https://www.testvalley.gov.uk/assets/attach/7403/Local%20Plan%20Issues%20and%20Options%20FINAL.pdf |  | QTR 1 2020 | Refined Issues and Options | 2020-02-01 | 2020-07-08 | 2020-08-28 | https://www.testvalley.gov.uk/planning-and-building/planningpolicy/local-development-framework/next-local-plan-refined-issues-and-options-consultation-2020 |  | Q1 2022 | Reg 18 (Stage 1) re-freshed consultation | 2022-02-01 | 2022-02-01 | 2022-04-08 | https://www.testvalley.gov.uk/planning-and-building/planningpolicy/local-development-framework/draft-local-plan-2040?chapter=2#comments |  | Q4 2022 | Reg 18 (Stage 2) re-freshed consultation | 2022-11-01 |  |  |  |  | Q4 2023 | 2023-11-01 |  | Q3 2024 | 2024-08-01 |  | Q3 2025 | 2025-08-01 |  | May 2022 version of tt on website corroborates LDS | Reg 18 consultation refreshed with first Reg 18 in Q1 2022 (ran until 8 April 2022) and second Reg 18 in Q4 2022. Publication scheduled for Q4 2023 (was Q3 2022); Submission now Q3 2024 (was Q3 2023); Adoption now expected Q3 2025 (was Q3 2024). |  | 2022-08-11 | 2021-11-18 | Robert Putnam | 2022-08-08 | 2022-05-05 | Robert Putnam |  |  | VisualPing
E07000077 | Uttlesford | New Local Plan 2020-2040 | 2192 | 2020 | 2040 | N | N | none | YES | previous plan found unsound and withdrawn; further round of consultations | [9 empty] | Yes | Yes | LDS Document |  | https://www.uttlesford.gov.uk/article/4969/Local-Plan-timetable | https://www.uttlesford.gov.uk/media/10546/Local-Development-Scheme-2022/pdf/LDS_update_July_2022_51ktcfk7azb1.pdf?m=637931338041330000 |  | 2022-07-01 | Oct 2020 | Extended Issues & Options | 2020-10-01 | 2022-11-01 | 2021-04-01 | https://www.uttlesford.gov.uk/Consultation-and-the-Community-Stakeholder-Forum |  | 2 Nov 2022 to 12 Dec 2022 | Preferred Options | 2022-11-01 |  |  | https://www.uttlesford.gov.uk/Consultation-and-the-Community-Stakeholder-Forum | [15 empty] | Nov - Dec 2023 | 2023-11-01 |  | May 2024 | 2024-05-01 |  | March 2025 | 2025-03-01 |  | An updated Local Development Scheme is being taken to the Council’s cabinet in July 2022. It is anticipated that this will result in the regulation 18 consultation being pushed back to the autumn and knock-on consequences to the regulation 19 publication period. | New July LDS and timetable: Preferred Options: Nov - Dec 2022 (was Mar - April 2022); Publication now Nov - Dec 2023 (was Mar-April 2023); Submission now May 2024 (was August 2023); and Adoption now March 2025 (was July 2024). |  |  | 2022-07-11 | Robert Putnam |  | 2022-07-11 | Robert Putnam | 2022-07-08
E07000180 | Vale of White Horse | Joint Local Plan 2041 | 2114 | 2021 | 2041 | N | Y | 14 December 2016 (as modified by Part 2 Plan adopted 9 October 2019) | YES | Covid-19 Nitrates (March 2022) | [7 empty] | 2021-12-03 | Adopted Plan Parts 1 and 2 up-to-date | Yes | Yes | LDS Document |  | https://www.whitehorsedc.gov.uk/vale-of-white-horse-district-council/planning-and-development/local-plan-and-planning-policies/local-plan-2041/ | https://www.whitehorsedc.gov.uk/wp-content/uploads/sites/3/2022/05/Joint-LDS-May-22-Final-Version.pdf |  | 2022-05-01 | 12 May 2022 to 23 June 2022 | Joint Local Plan Issues consultation (not scheduled in LDS) | 2022-06-23 | 2022-05-12 | 2022-06-23 | https://storymaps.arcgis.com/collections/54bfeeae245242d9b3b7cd1e6b049388 |  | Jan/Feb 2023 | Preferred Options/Draft Plan | 2023-01-01 | [18 empty] | July/August 2023 | 2023-07-01 |  | January 2024 | 2024-01-01 |  | October 2024 | 2024-10-01 |  | Progress impacted by Covid-19. Working on Joint Local Plan with South Oxfordshire Council on a joint plan between these two councils for the first time. The Oxfordshire authorities have ceased working on the Oxfordshire Joint Strategic Spatial Plan 2050. | New Joint Local Plan to 2041 between Vale of White Horse and South Oxfordshire. Issues and Scope (Reg 18) May/June 2022; Preferred Options (Reg 18) Jan/Feb 2023; Reg 19 July/August 2023; Submission Jan 2024; Adoption Oct 2024 | Issues and Scope (Reg 18) May/June 2022; Preferred Options (Reg 18) Jan/Feb 2023; Reg 19 July/August 2023; Submission Jan 2024; Adoption Oct 2024 | 2022-04-05 | 2022-07-07 | Robert Putnam | 2022-07-07 | 2022-06-01 | Robert Putnam | 2021-04-30 |  | VisualPing
E07000180 | Vale of White Horse | Oxfordshire Joint Plan 2050 | 2085 | 2020 | 2050 | N | Y | 14 December 2016 (as modified by Part 2 Plan adopted 9 October 2019) | YES | Covid-19 Nitrates (March 2022) | [6 empty] | 2022-08-01 |  |  | Yes | Yes | LDS Document |  | https://www.oxford.gov.uk/downloads/file/7340/local_development_scheme_2020-25 | https://www.oxford.gov.uk/download/downloads/id/7340/local_development_scheme_2020-25.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/LDS%20&%20Reg%2018%20Monitoring/LDS%20Screenshots/OXF2020%20-%20Oxford%20City%20LDS%20July%202020.PNG | 2021-05-01 | Feb/March 2019 | First Stage - Introducing the Oxfordshire Plan | 2019-02-01 | 2019-02-11 | 2019-03-25 | https://oxfordshireplan.inconsult.uk/consult.ti/Oxfordshire_Plan_Intro/consultationHome |  | Summer 2021 | Spatial Growth Options (including scale and Broad Locations of Growth) (Reg. 18 part2) | 2021-07-01 | 2021-07-30 | 2021-10-08 | https://oxfordshireplan.inconsult.uk/Call_for_Ideas_2021/consultationHome | [15 empty] | July 2023 | 2023-07-01 |  | Jan 2024 | 2024-01-01 |  | TBC | TBC |  | A PINS Advisory Visit has taken place (December 2021) which recommended that Oxford decide on a preferred approach. This approach needs to be agreed before Reg 19 with the possibility of a third Reg 18 required. The Housing Deal is likely to be revised to allow more time for the Plan to progress with Submission just before December 2023 looking likely. Kevin Reid and Dave J to meet Oxfordshire 2050 team Summer 2022 to discuss progress and request for dates made to Oxfordshire 2050 team on 21/6/2022. |  | PINS Intel: Reg 19 expected July 2023; Submission expected Jan 2024 work ceased on plan August 2022 | 2021-03-01 | 2021-10-14 | Robert Putnam | 2021-08-19 | 2022-07-22 | Robert Putnam | 2022-06-27 | work ceased on plan August 2022 | VisualPing
E08000036 | Wakefield | Wakefield District Local Plan | 2070 | 2017 | 2036 | N | N | 2009-04-15 | YES | COVID-19 |  |  | 2020-10-29 | 2021-05-04 | [5 empty] | Yes | Yes | LDS Document |  | http://www.wakefield.gov.uk/planning/policy/emerging-local-plan-2036/development-scheme-progress | http://www.wakefield.gov.uk/Documents/planning/planning-policy/local-plan/local-development-scheme/local-development-scheme-2017.pdf | https://teams.microsoft.com/_#/png/viewer/teams/https:~2F~2Fmhclg.sharepoint.com~2Fsites~2FDevelopmentPlans~2FShared%20Documents~2FData%20and%20Analysis~2FPlanning%20Data%20Unit~2FData%20Project~2FShort-term%20Solution~2FLDS%20Approach~2FLDS%20screen%20captures~2FWAK17%20-%20Wakefield%20LDS%202017.PNG?threadId=19:02cfc1d922c64c5584e5731b4a607ece@thread.skype&baseUrl=https:~2F~2Fmhclg.sharepoint.com~2Fsites~2FDevelopmentPlans&fileId=D7F48A50-5FC9-445A-AC3D-639169E95361&ctx=files&viewerAction=view | 2021-09-01 | July to December 2017 |  | 2017-09-01 | 2017-10-26 | 2017-12-06 | http://www.wakefield.gov.uk/Documents/planning/planning-policy/local-plan/2036/local-plan-early-engagement-document-final-october-2017.pdf |  | September to October 2018 |  | 2018-09-01 | 2019-01-10 | 2019-02-20 | http://www.wakefield.gov.uk/ldp2036/Initial%20Draft_Volume%201_Development%20Strategy,%20Strategic%20and%20Local%20Policies%20Web%20Copy.pdf | [15 empty] | July to August 2019 | 2019-07-01 | 2020-10-29 | November 2019 | 2019-11-01 | 2021-05-04 | Nov 2022 | 2022-11-01 |  | Examination hearings completed 15 December 2021. Further work/information is required to support the policies and proposals in the Submitted Plan. LPA to liaise with Inspector about way forward (as at 3 Feb 2022). |  |  | 2022-05-03 | 2021-11-19 | Robert Putnam |  | 2021-11-19 | Robert Putnam | 2022-02-03 | S | Submitted May 2021
E06000007 | Warrington | Warrington Local Plan | 2092 | 2021 | 2038 | N | N | 2014-07-21 | YES | White Paper & Covid-19 |  |  | 2019-04-25 | 2022-04-22 | [5 empty] | Yes | Yes | LDS Document |  | https://www.warrington.gov.uk/info/200564/planning-policy/1903/local-plan/2 | https://www.warrington.gov.uk/download/downloads/id/19065/local-development-scheme.pdf | https://mhclg.sharepoint.com/:i:/s/DevelopmentPlans/EcrYlqs3zJBLuS3DBTcQ10wBaaAy6VNDjKKK58x5nQiwUw?e=nKGYxj | 2019-03-01 | Oct - Dec 2016 |  | 2016-11-01 |  |  |  |  | June - Sept 2017 |  | 2017-07-01 | [18 empty] | April 2019 | 2019-04-01 | 2019-04-25 | October 2019 | 2019-10-01 | 2022-04-22 | December 2020 | 2020-12-01 |  | Warrington Borough Council say it is pausing work on its local plan until next summer (2021) in response to the white paper changes along with the revised standard housing need method and the impact of Covid-19. Leader of the Labour-run council Russ Bowden said the two sets of planning changes "mean that we are currently in a period of uncertainty", adding that it would be "inappropriate to move ahead with the submission of our current plan to the planning inspector at this time”. | Published April 2019 but work now paused. Submitted 22 April 2022. |  | 2020-11-13 |  | Robert Putnam |  |  |  | 2021-11-16 | S | Submitted April 2022
E07000103 | Watford | Watford Local Plan 2021-2038 | 2251 | 2021 | 2038 | N | N | 2013-01-30 | YES | COVID-19 |  |  | 2021-01-18 | 2021-08-06 | [5 empty] | Yes | Yes | LDS Document |  | https://www.watfordlocalplan.co.uk/timeline | https://fd198c31-76ed-460c-8b90-4dac3f151e20.filesusr.com/ugd/b57e7b_2fb16b33f67041e182de60bf18fe5c42.pdf |  | 2021-07-01 | September - October 2018 | Issues & Options | 2018-09-01 | 2018-09-07 | 2018-10-19 | https://docs.wixstatic.com/ugd/b57e7b_e5856a36deb643f6a4d875c203c136e3.pdf |  | September - October 2019 | Preferred Options | 2019-09-01 | 2019-09-27 | 2019-11-08 | https://www.watfordlocalplan.co.uk/first-draft-local-plan1 | [15 empty] | Jan 2021 | 2021-01-01 | 2021-01-18 | July 2021 | 2021-07-01 | 2021-08-06 | June 2022 | 2022-06-01 |  |  | Published Jan 2021. Consultation period on submission version of plan (Reg 19) ran from 18 January - 18 March 2021. New timetable in July 2021 LDS, shows submission expected July 2021 (was June 2021) and adoption June 2022 (was February 2022). Plan now submitted 6 August 2021. | The first consultation on the document is due to take place in early September. | 2021-01-21 | 2021-08-09 | Robert Putnam |  | 2021-09-01 |  | 2021-08-09 | S | Plan Submitted Aug 2021
E07000065 | Wealden | Wealden Local Plan | 1948 | 2018 | 2038 | N | N | 2012-11-28 | YES | Previous plan withdrawn | [9 empty] | Yes | Yes | LDS Document |  | https://www.wealden.gov.uk/planning-and-building-control/planning-policy/planning-policy-documents/local-development-scheme/ | https://www.wealden.gov.uk/UploadedFiles/Final-LDS-1.pdf |  | 2020-07-22 | Spring 2022 | April 2022 | [26 empty] | Winter 2022 | 2023-01-01 |  | Spring 2023 | 2023-04-01 |  | Winter 2023 | 2024-01-01 |  | Uncertainity over the implications of the planning reform | Previous Plan withdrawn from examination Feb 2020. July 2020 LDS. Reg 18 yet to start. First and only Reg 18 scheduled for Spring 2022; Publication Winter 2022; Submission Spring 2023; Adoption (an unrealistic) Winter 2023. Uncertainty over the implications of the planning reforms. PINS Intel (August 2022) corroborates TT. |  | 2021-10-11 | 2021-04-01 | Robert Putnam | 2022-08-24 | 2021-04-01 | Robert Putnam | 2022-08-18 |  | VisualPing
E06000037 | West Berkshire | West Berkshire Local Plan Review to 2039 | 2162 | 2024 | 2039 | N | N | 2012-07-16 | YES | NPPF (July 2021) Nitrates (March 2022) | [9 empty] | Yes | Yes | LDS Document |  | https://info.westberks.gov.uk/lds | https://info.westberks.gov.uk/CHttpHandler.ashx?id=52706&p=0 |  | 2022-06-01 | Dec 2017 - Nov 2019 | Scope and content consultation |  | 2018-02-12 | 2018-03-26 | https://info.westberks.gov.uk/localplanreview2036 |  |  | second round of consultation: vision |  | 2018-11-09 | 2018-12-21 | https://info.westberks.gov.uk/CHttpHandler.ashx?id=46409&p=0 |  | 2020-12-11 | emerging draft of the Local Plan Review (Reg 18) | 2020-12-01 | 2020-12-11 | 2021-02-05 | https://info.westberks.gov.uk/localplanreview2037 | [8 empty] | Dec 2022 | 2022-12-01 |  | March 2023 | 2023-03-01 |  | Sept 2024 | 2024-09-01 |  | Announced on 18 August 2021 that work is postponed due to changes to NPPF. https://info.westberks.gov.uk/article/38461/Council-obliged-to-postpone-local-plan-review | New June 2022 timetable: Reg 19 scheduled for December 2022; Submission March 2023; Adoption Sept 2024 |  | 2022-08-31 | 2022-08-09 | Robert Putnam | 2022-09-02 | 2022-08-09 | Robert Putnam |  |  | VisualPing
E07000047 | West Devon | The Plymouth and South West Devon Plan Review | 1819 | 2014 | 2034 | N | Y | 2019-03-26 | YES | COVID-19 | [9 empty] | FALSE | No | None |  | https://www.westdevon.gov.uk/article/3457/Plymouth-and-South-West-Devon-Joint-Local-Plan | [33 empty] | 2017-03-15 | May 2017 | 2017-05-01 | 2017-07-31 |  |  | 2019-03-26 | Plymouth and South West Devon Joint Local Plan 2014-2034 adopted by West Devon BC on 26 March 2019 (and adopted by South Hams DC on 21 March 2019). The impact of COVID-19 has disrupted planning services across the JLP area at each respective authority. |  | The first version of the Plymouth and South West Devon Local Development Scheme was published in October 2019 but has become out of date. The Joint Local Plan Councils are committed to the delivery of the plan, and to keeping its policies fully up to date at all times. A review of the Joint Local Plan will be completed by 26 March 2024 at the latest. A new revised Local Development Scheme setting out the detailed timetable for the review will be produced once there is clarity about changes to the planning system. | 2022-08-08 |  | Robert Putnam |  |  |  | 2022-08-08 | A | adopted March 2019
E07000127 | West Lancashire | West Lancashire Local Plan 2023 - 2040 | 2282 | 2023 | 2040 | N | N | 2013-10-16 | YES | White Paper Covid-19 (work recommenced March 2021) | [8 empty] | Previous review stopped and now working on preparing a new Local Plan 2023-2040 recorded here | Yes | Yes | LDS Document |  | https://www.westlancs.gov.uk/planning/planning-policy/the-local-plan/the-local-plan-2023-2040.aspx | https://www.westlancs.gov.uk/media/546675/lds-2022-03_final-appendix-a-to-2022-03-cabinet-report.pdf |  | 2022-03-01 | Q4 2021 | Scope, Issues & Options | 2021-11-01 | 2021-11-01 | 2022-01-01 | https://www.westlancs.gov.uk/planning/planning-policy/the-local-plan/the-local-plan-2023-2040.aspx |  | July - Sept 2022 | Policies, Development Requirements & Site Allocations Consultation | 2022-07-01 | [18 empty] | July - Sept 2024 | 2024-07-01 |  | Oct 2024 | 2024-10-01 |  | July 2025 | 2025-07-01 |  | The current adopted Local Plan for West Lancashire is the Local Plan 2012-2027. In 2016, the council began the Local Plan Review (2050) which was intended to guide development for 38 years, from 2012 to 2050. However, this plan was effectively 'withdrawn' in September 2019 to give the authority more time to consider the best proposals for the future of West Lancashire. Instead, the council authority is now preparing a new Local Plan and an updated LDS was published in March 2022. | Regulation 18 Consultation November 2021 - January 2022; Policies, Development Requirements & Site Allocations Consultation July – September 2023; Publication / Pre-Submission July – September 2024; Submission to Planning Inspectorate October 2024; Examination in Public (incl. Hearings) October 2024 – June 2025; Adoption July 2025. *** PINS intel April 2022: Submission expected December 2024 (March LDS said Oct 2024) |  | 2022-08-30 | 2022-04-14 | Robert Putnam |  | 2022-04-14 | Robert Putnam | 2022-07-21 |  | VisualPing
E07000245 | West Suffolk | West Suffolk Local Plan Review | 2172 | 2020 | 2041 | N | N | new LPA | YES | Covid-19 | [9 empty] | Yes | Yes | Web-page timetable |  | https://www.westsuffolk.gov.uk/planning/Planning_Policies/supportinginformation.cfm | https://www.westsuffolk.gov.uk/planning/Planning_Policies/supportinginformation.cfm |  | 2021-07-01 | Oct - Dec 2020 | Issues & Options | 2020-11-01 | 2020-10-01 | 2020-12-01 | https://westsuffolk.inconsult.uk/consult.ti/system/listConsultations?type=all |  | March - May 2022 | Preferred Options | 2022-03-01 | [18 empty] | May 2023 | 2023-05-01 |  | Oct 2023 | 2023-10-01 |  | July 2024 | 2024-07-01 |  | New authority from April 2019. Formerly Forest Heath; and St Edmundsbury Councils. Note NOT unitarised. In light of the current COVID-19 situation the Regulation 18 - issues and options consultation, planned for May 2020 was delayed to Oct 2020. Updated LDS published in January 2021. | Reg 18 consultation ongoing with second consultation (Preferred Options) scheduled for March - May 2022 (was Jan - March 2022). Publication now Feb - April 2023 (was Oct/Nov 2022). Submission June 2023 (was Feb 2023); Adoption July 2024. *** PINS Intel: Reg 19 May 2023; Submission Oct 2023 |  | 2021-11-19 | 2021-09-13 | Robert Putnam |  | 2022-07-22 | Robert Putnam |  |  | VisualPing
E06000054 | Wiltshire | Wiltshire Local Plan Review | 2026 | 2016 | 2036 | N | N | 2015-01-20 | YES | Nitrates (since 2018) | [9 empty] | Yes | Yes | LDS Document |  | https://www.wiltshire.gov.uk/planning-policy-lds | https://www.wiltshire.gov.uk/media/7716/Local-Development-Scheme-2021/pdf/Local_Development_Scheme_2021.pdf?m=637747199905270000 |  | 2021-11-01 | Nov 2017 | Issues & Options | 2017-11-01 | 2017-11-07 | 2017-12-19 | http://www.wiltshire.gov.uk/spp-consultation-report-nov-dec-2017.pdf |  | Dec 2020/Jan 2021 | revised scope and emerging strategy | 2020-12-01 | 2021-01-13 | 2021-03-09 | https://www.wiltshire.gov.uk/planning-policy-local-plan-review-consultation | [15 empty] | QTR 4 2022 to QTR 2 2023 | 2022-11-01 |  | QTR 2 2023 | 2023-05-01 |  | end QTR 4 2023 | 2023-12-01 |  | No longer working on a Joint Spatial Framework with Swindon. | Reg 18 consultations completed. Publication of plan for pre‐submission consultation and preparation for submission following consultation - Qtr 4 2022 - Qtr 2 2023; Submission to Secretary of State - Qtr 2 2023; Examination (including hearing and receipt of Inspector’s report) - Commencing Qtr 2 2023; Adoption - End Qtr 4 2023 |  | 2022-09-02 | 2021-12-10 | Robert Putnam | 2022-09-02 | 2021-12-10 | Robert Putnam |  |  | VisualPing
E07000094 | Winchester | Winchester District Local Plan 2018 - 2039 | 2163 | 2018 | 2039 | N | N | 2013-03-20 | YES | White Paper Nitrates (since 2018) | [9 empty] | Yes | Yes | LDS Document |  | https://www.winchester.gov.uk/planning-policy/winchester-district-local-plan-2018-2038-emerging/local-development-scheme | https://www.winchester.gov.uk/assets/attach/29850/CAB3302-APPENDIX-LDS-July-2021-2-.pdf |  | 2021-07-01 | Mid 2018 | Local Plan Launch Consultation | 2018-12-01 | 2018-08-10 | 2018-09-21 | https://www.winchester.gov.uk/assets/attach/16465/Local%20Plan%20Launch%20Consultation%20Paper%20Version.pdf |  | March/April 2021 | Strategic Issues and Priorities (Reg 18) and draft sustainability appraisal | 2021-03-01 | 2021-02-15 | 2021-04-12 | https://winchester.citizenspace.com/policy-and-planning/wcc-local-plan-sip/ |  | Nov 2022 - Dec 2022 | Consultation on the Reg 18 Local Plan | 2022-11-01 | [11 empty] | Aug - Sept 2023 | 2023-08-01 |  | November 2023 | 2023-11-01 |  | July/August 2024 | 2024-07-01 |  | New July 2021 provides a further Reg 18 stage (consultation on local plan). Reg 19 is now Aug-Sept 2023 (was December 2021); Submission November 2023 (was May 2022); Examination Feb/March 2024; Consultation on proposed MM May 2024; Adoption July/August 2024 (was Jan 2023). Reg 18 on draft plan now delayed to Nov - Dec 2022. | New July 2021 provides a further Reg 18 stage (consultation on local plan) in August - September 2022. Reg 19 is now Aug-Sept 2023 (was December 2021); Submission November 2023 (was May 2022); Adoption July/August 2024 (was Jan 2023). Reg 18 on draft plan now delayed to Nov - Dec 2022. |  | 2022-05-31 | 2021-07-23 | Robert Putnam | 2022-06-27 | 2022-07-06 | Robert Putnam | 2021-07-23 |  | VisualPing; e-mail
E08000015 | Wirral | single Wirral Local Plan | 2025 | 2021 | 2037 | N | N | none | YES | COVID-19 | [9 empty] | Yes | Yes | LDS Document |  | https://www.wirral.gov.uk/planning-and-building/local-plans-and-planning-policy/local-plans/local-development-scheme | https://www.wirral.gov.uk/sites/default/files/all/planning%20and%20building/Local%20plans%20and%20planning%20policy/Local%20plans/Local%20Development%20Scheme/AdoptedLocalDevelopmentSchemeReviewJanuary2022.pdf |  | 2022-02-02 | Jan 2010 | Spatial Options | 2010-01-01 | 2010-01-11 | 2010-03-05 | https://www.wirral.gov.uk/sites/default/files/all/planning%20and%20building/Local%20plans%20and%20planning%20policy/Local%20plans/Core%20strategy%20local%20plan/Consultation%20on%20Spatial%20Options/Wirral%20Core%20Strategy%20Spatial%20Options%20Consultation%20Letter.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Wirral%20Spatial%20Options%20Reg%2018%20Jan%202010.PNG | Jan 2012 | Settlement Areas | 2012-01-01 | 2012-01-24 | 2012-03-12 | https://www.wirral.gov.uk/sites/default/files/all/planning%20and%20building/Local%20plans%20and%20planning%20policy/Local%20plans/Core%20strategy%20local%20plan/Consultation%20on%20Settlement%20Area%20Policies/SANotificationLetter24Jan12Header.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Wirral%20Settlement%20Areas%20Reg%2018%20Jan%202012.PNG | Jan - Feb 2020 | Local Plan 2020-2035 Issues & Options | 2020-01-01 | 2020-01-27 | 2020-04-27 | https://www.wirral.gov.uk/sites/default/files/all/planning%20and%20building/Local%20plans%20and%20planning%20policy/Local%20plans/Core%20strategy%20local%20plan/New%20Local%20Plan/Issues%20and%20Options%20Only%20January%202020%20Website.pdf | [8 empty] | March - June 2022 | 2022-03-01 | 2022-05-09 | Oct 2022 | 2022-10-01 |  | Mid - Late 2023 | 2023-06-01 |  | This current document replaces the Local Development Scheme adopted by the Council on 14th October 2020. It has become necessary to review the Local Development Scheme because of changes to the timetable for the Local Plan arising from the implications of Covid 19 which originally delayed the commissioning and completion of several evidence base studies. including work commissioned in response to submissions made at the Regulation 18 consultation in early 2020. In addition, in late summer 2021 the Council had to procure at short notice new consultants to undertake the viability assessment of the Local Plan following the withdrawal of the previously appointed consultants due to unforeseen circumstances which meant they would be unable to complete their work to the agreed timetable. This has had the knock-on effect of delaying the preparation of the Regulation 19 stage of the Local Plan. | Third Reg 18 consultation closed April 2020. Delay to publication date scheduled for July-September 2020 caused by Covid-19 and had been expected Feb 2021 but missed. Local Plan period extended to 2037. New LDS Feb 2022. Reg 19 now March - June 2022. PINS Intel: Submission October 2022. |  | 2022-04-22 | 2022-03-28 | Robert Putnam |  | 2022-08-10 | Robert Putnam | 2021-09-06 | P | VisualPing. Published May 2022.
E06000041 | Wokingham | Local Plan Update | 1932 | 2018 | 2038 | N | N | 2010-01-29 | YES | OTHER | PAS | [8 empty] | Yes | Yes | LDS Document |  | https://www.wokingham.gov.uk/planning-policy/planning-policy-information/local-plan-update/ | https://www.wokingham.gov.uk/EasySiteWeb/GatewayLink.aspx?alId=599969 |  | 2021-07-01 | Aug 2016 | Issues & Options | 2016-08-01 | 2016-08-04 | 2016-09-30 | http://www.wokingham.gov.uk/localplanupdate |  | Nov 2018 | Homes for the Future | 2018-11-01 | 2018-11-12 | 2019-02-22 | https://www.wokingham.gov.uk/planning-policy/planning-policy-information/local-plan-update/# |  | Feb - March 2020 | Draft Plan Consultation | 2020-02-01 | 2020-02-03 | 2020-04-03 | https://www.wokingham.gov.uk/planning-policy/planning-policy-information/draft-local-plan-consultation/ |  | 2021-11-01 | Revised Growth Strategy | 2021-11-01 | 2021-11-22 | 2022-01-24 | https://www.wokingham.gov.uk/planning-policy/planning-policy-information/local-plan-update/ |  | Sept 2022 | 2022-09-01 |  | April 2023 | 2023-04-01 |  | TBC | TBC |  |  | PINS Intel (April 2022): Reg 19 expected Sept 2022; Submission April 2023 |  | 2022-06-01 | 2022-07-29 | Robert Putnam |  | 2022-07-29 | Robert Putnam |  |  | VisualPing
E07000237 | Worcester | South Worcestershire Development Plan Review | 2137 | 2021 | 2041 | N | Y | 2016-02-25 | YES | Covid-19 | [9 empty] | Yes | Yes | LDS Document |  | https://www.swdevelopmentplan.org/publications/local-development-scheme | https://www.swdevelopmentplan.org/component/fileman/file/Documents/South%20Worcestershire%20Development%20Plan/Publications/LDS/LDS%20Sept%202021%20-%20Worcester%20City%20Council.pdf?routed=1&container=fileman-files |  | 2021-10-01 | Nov - December 2018 | Issues & Options | 2018-11-01 | 2018-11-05 | 2018-12-17 | https://www.swdevelopmentplan.org/wp-content/uploads/2018/11/SWDPR-IO-Nov18-RFS.pdf | https://mhclg.sharepoint.com/sites/DevelopmentPlans/Shared%20Documents/Data%20and%20Analysis/Planning%20Data%20Unit/Reg%2018%20monitoring/Screenshots/Malvern%20Hills%20Issues%20&%20Options%20Nov%202018.PNG | Nov - December 2019 | Preferred Options | 2019-11-01 | 2019-11-04 | 2019-12-16 | https://www.swdevelopmentplan.org/wp-content/uploads/2018/11/SWDPR-IO-Nov18-RFS.pdf |  | March - April 2021 | Further Preferred Options | 2021-03-01 | 2021-03-01 | 2021-04-19 | https://www.swdevelopmentplan.org/swdp-review/swdp-review-regulation-18-3-sa-consultation | [8 empty] | Nov 2022 | 2022-11-01 |  | March 2023 | 2023-03-01 |  | TBC | TBC |  |  | PINS Intel (July 2022): Reg 19 expected November 2022; Submission March 2023. |  | 2021-02-25 | 2022-01-28 | Robert Putnam |  | 2022-07-29 | Robert Putnam |  |  | Visualping
E07000229 | Worthing | Worthing Local Plan | 2252 | 2020 | 2036 | N | N | 2011-04-12 | YES | COVID-19 |  |  | 2021-01-26 | 2021-06-11 | [5 empty] | Yes | Yes | LDS Document |  | https://www.adur-worthing.gov.uk/worthing-ldf/local-development-scheme/ | https://democracy.adur-worthing.gov.uk/documents/g1516/Public%20reports%20pack%2020th-Jan-2021%2018.30%20Worthing%20Planning%20Committee.pdf?T=10 |  | 2021-01-01 | Autumn/Winter 2018 | Preferred Options | 2018-10-01 | 2018-10-31 | 2018-12-12 | https://www.adur-worthing.gov.uk/media/media,151142,en.pdf | [22 empty] | Quarter 1 2021 | 2021-02-01 | 2021-01-26 | Quarter 2 2021 | 2021-05-01 | 2021-06-01 | Quarter 1 2022 | 2022-02-01 |  | Following examination MM introduce a housing trajectory. The requirement is short of OAHN (see Policy SS2). 3,672 overall or 230 DPA. |  |  | 2021-01-27 |  | Robert Putnam |  |  |  | 2021-03-05 | S | Submitted June 2021
Note on AB94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: but amended by website TT

## LISTS (hidden)
Yes | LDS Document
Yes, but TT refers to adopted Plan | Web-page timetable
Yes, but refers to something else | Other
No | None
Robert Putnam
Max Laverack
Shannon Franklin
Sarah Hunt
Rachael Lee
Vicky Engelke
Greg Foster
Zoe Adams
Robert Putnam
Max Laverack
Shannon Franklin
Sarah Hunt
Rachael Lee
Vicky Engelke
Greg Foster
Zoe Adams
YES
NO
NO but expected July 2020